## Sheet1
Insurance-Agency-Performance-Analysis & Agency segmentation
Project Team members : Amit Kumar Raut, Brown Varghese, Krunal Panchal, Luis Davalos, Radha Mahalingam
Porject Tasks
| Sno. | Activity Name | Owner | Team assisting | Duration | Start | End | Status | Comments
| 1 | Create Slack Channel | Radha |  |  | 2019-07-16 | 2019-07-16 | Complete
| 2 | Create Github Repository | Brown |  |  | 2019-07-17 | 2019-07-17 | Complete
| 3 | Project Idea Finalization | Amit, Luis, Brown, Krunal, Radha |  |  | 2019-07-16 | 2019-07-16 | Complete
|  | Data Sources | Radha |  |  | 2019-07-16 | 2019-07-16 | Complete | From Kaggle, US Census Website
| 4 | Project Requirement Definition | Radha | Amit, Luis, Krunal, Brown |  | 2019-07-18 | 2019-07-18 | Complete
| 5 | Technical specification | Radha | Amit, Luis, Krunal, Brown |  | 2019-07-18 | 2019-07-20 | In Progress
|  | Data collection, data cleaning & data transformation to be ready for ML | Radha | Amit |  | 2019-07-17 | 2019-07-18 | In Progress
|  | Machine Learning Specification | All |  |  | 2019-07-18 | 2019-07-18 | Not Started
|  | Data Visualization specification | Brown | Krunal, Luis |  | 2019-07-17 | 2019-07-18 | In Progress
|  | ML End to End execution pipeline specification | All |  |  | 2019-07-18 | 2019-07-20 | Not Started
| 8 | Writing data Cleaning & Transform Program | Radha | Amit |  | 2019-07-17 | 2019-07-19 | In Progress
| 9 | Writing ML Program | All |  |  | 2019-07-18 | 2019-07-19 | Not Started
| 10 | Writing Data Visualization program | Brown | Luis, Krunal, |  | 2019-07-17 | 2019-07-19 | In Progress
| 11 | Writing the Final Report | Radha | Amit, Luis, Krunal, Brown |  | 2019-07-20 | 2019-07-20 | Not Started
| 12 | Creating presentation material | Krunal | Amit, Luis, Radha, Brown |  | 2019-07-20 | 2019-07-22 | Not Started